Accredited Standards Committee
X3, Information Processing Systems

Doc: 	X3T10.1/95-140R0
Date:	April 3, 1995
Project:	
Ref Doc.:	
Reply to:	John Scheible

To: 	   	X3T10.1 Membership
From:	John Scheible

Subject: X3T10.1 document schedule

The estimated document schedule for the SSA-S2P, SSA-TL1, and SSA-PH1 is as follows.

- March 30, 95 - Editors meetings Austin (2 days) , general work and generate project proposals.

- April 20, 95 - Editors meeting San Jose (2 days), work on document organization.

- April 26, 95 - X3T10.1 working group.  Issue closure (major technical issues resolved).  The priority for this week is the SSA-UIG 94 and 95 documents, with X3T10.1 getting only 1 day.  Review project proposals.

- May 9, 95 - X3T10.1 plenary (1 day).  Approve Working group items and project proposals.

- May 23, 95 - Electronic version of the set of documents (SSA-S2P, SSA-TL1, SSA-PH1) available.

- June 28, 95 - X3T10.1 working group and plenary (3 days).  Technical closure (final date for technical proposals, approved with final wording).

- June 29,30,1 - SSA Editors meeting in San Jose (3 days, Thu, Fri, Sat).

- July 21, 94 - Electronic version of the technically complete documents (SSA-S2P, SSA-TL1, SSA-PH1)

- August 30, 95 - X3T10.1 working group and plenary (2 days).  Class on documents and final editing changes.

- September 13, 95 - Mailing for X3T10.1 letter ballot.

- October 20, 95 - Closure of X3T10.1 letter ballot.

- November 1, 95 - X3T10.1 working group and plenary (3 days).  Letter ballot review comment resolution, final wording must be decided at working group meetings.

- November 17, 95 - Electronic distribution of documents with letter ballot comment resolution included.

- December 13, 95 - X3T10.1 working group and plenary (2 days).  Final editing changes at working groups. Plenary approves comment resolution level of documents and vote to forward documents to X3T10.

- Hopefully time is available for Christmas

- January 11, 96 - Request X3T10 letter ballot

- January 25, 96 - Letter ballot to X3T10, X3T10 letter ballot level of documents available.

- February 28, 96 - Working group and plenary (2 days).  Partial resolution of X3T10 comments.

- March 6, 96 - Letter ballot to X3T10 closes

- May 1, 96 - X3T10.1 working group and plenary (3 days).  X3T10 letter ballot review comment resolution, final wording must be decided at working group meetings.  Vote to accept comment resolution.

- May 9, 96 - Review letter ballot comment resolution at X3T10 plenary.

- May 23, 96 - X3T10 comment resolution level of document available for mailing.

- July 18, 96 - Request X3T10 vote to forward documents to X3 for public review.

- June 26, 96 - X3T10.1 working group and plenary (2 days) available for SSA-S3P, SSA-TL2, SSA-PH2.

- August 28, 96 - X3T10.1 working group and plenary (2 days) available for SSA-S3P, SSA-TL2, SSA-PH2.

- Oct 14, 96 - Hopefully public review closes

- October 30, 96 - X3T10.1 working group and plenary (3 days).  Public review comment resolution, final wording must be decided at working group meetings.  Vote to accept public review comment resolution.

- November 7, 96 - Present public review comment resolution to X3T10.  X3T10 may invoke two week rule and add 2 months to approval.  If any substantive technical changes (subjective) were done, another public review is needed.

The key dates for the SSA-S2P, SSA-TL1, and SSA-PH1 are:

- May 9, 1995 - Project proposals submitted to X3T10

- July 14, 1995 - Documents technically complete

- September 13, 1995 - X3T10.1 Letter ballot

- December 13, 1995 - X3T10.1 letter ballot comment resolution approved

- January 25, 1996 - X3T10 Letter ballot

- May 9, 1996 - X3T10 letter ballot comment resolution approved by X3T10

- July 18, 96 - Forward to X3 for public review

- October 30, 96 - Public review comment resolution

- November 7, 96 - Approval of public review comment resolution by X3T10

- March 1997 - Publication best case

Sincerely,

John Scheible
Voice:	(512) 823-8208
FAX: 	(512) 823-0758
Email:	Scheible@vnet.ibm.com