## Sheet1
SAT-2 Work Items List
Issue # | Description | Owner | Status
2 | ATAPI Translations | Mark Overby
3 | Reporting ATA host capabilities/control through mode page (e.g., NCQ Control) | Mark Overby
4 | ATA Security Mode Translations | Curtis Stevens | Proposal Open (06-070)
5 | Describe LUN mappings in the presence of a port multiplier
6 | End to end data protection in SAT | Curtis Stevens
7 | Standard for SAT space reservation on ATA device | Jeff Wolford | Proposal Open (07-242)
8 | Reserve / Release (for Microsoft WHQL)
9 | Additional SATA PHY control in a SAS domain (SAS Protocol proposal) | Mark Overby
11 | Write long translation | Elliot / Wolford | Proposal Open (07-200)
12 | Non-v cache translation | Mark Overby
13 | NCQ Priority | Brad Besmer
14 | Log Counter translation (ATA device statistics log page) | Jeff Wolford
15 | Persistent Reservations (possibly dependent on 21)
16 | Device capacity change | Jim Hatfield
17 | SMART ATA Sub Command translations with log sense | Jeff Wolford
19 | ORWRITE Translation | Rob Elliott
20 | Tie COMMANDS CLEARED BY DEVICE SERVER to Clear Task Set | Mark Overby
21 | SATL Disk data format for stored information (e.g., mode pages) (coordinate with DDF 2 (SNIA)?) | Rob Elliott
22 | Saveable mode pages (standardized format) | Rob Elliott
24 | ATA Passthrough / UDMA / ATA8-AAM Clarifications | Mark Overby
25 | ATA Passthrough for READ LONG / WRITE LONG using SCSI transport | Curtis Stevens
26 | Error translation for IDNF | Jeff Wolford | Approved - To be incorporated(07-298)
27 | Additional Power Management Translations | Jeff Wolford
29 | DOWNLOAD MICROCODE Segemented Translation | Jeff Wolford
1 | Define ATA register query / update within a SAS domain |  | Deleted 11/7/06
10 | Application client-specific mode page translation | Mark Overby | Proposal Incorporated SAT-R1
18 | Large Physical Block Translation | Jim Hatfield / Rob Elliott | Proposal Incorporated SAT-R1
23 | SECURITY PROTOCOL translation (TCG) | Jim Hatfield | Proposal Incorporated SAT-R1
28 | RBC Translation |  | Deleted 10/17/07